## Roadmap v.1
Roadmap for the establishment of the High Anti-Corruption Court of Ukraine
Urgency | Key area | Activity | Implementing Authority | Time-frame | External Assistance | Available International Standards | Status of Progress
Phase 1 | Infrastructure | Decision by the Cabinet of Ministries of Ukraine on allocation of 2 separate premises to the SJA/HACC | Ministry of Economic Development and Trade/State Property Fund/Ministry of Justice/Minregion/SJA | November/December | No external assistance required |  | Cabinet of Ministers adopted the relevant decision
| Human Resources | Appointment of interim chief of staff of HACC | SJA | February/March | No external assistance required |  | Head of SJA has formally approached the HCJ to appoint interim CoS
| Finances and Budgeting | Interim Chief of Staff (CoS) to open a HACC account within state treasury | Interim Chief of Staff of HACC (ICoS) | February/March | No external assistance required
|  | Revision of 2019 draft budget by SJA with significant involvement of interim CoS (if timely appointed) and agreeing it with MoF | SJA/ICoS | November/December | No external assistance required | Checklist for promoting the quality of judges and courts, CEPEJ 2008 (section V.1) | Following the dicsussing beween the Ministry of Finance and SJA, it was agreed to allocate 318,1 mil UAH for HACC
| Infrastructure | Decision by Ministry of Regional Development, Building and Housing and Communal Services of Ukraine of transmition of 2 separate premises to the SJA/HACC | Ministry of Economic Development and Trade/State Property Fund/Ministry of Justice/Minregion/SJA | January/February | No external assistance required |  | SJA is in the negotiation process with respective bodies
Phase 2 |  | Conducting technical inspection and control measurements of HACC buildings in order to determine the real technical condition of these buildings and further development of a plan design | SJA/ICoS | February/March | External expert assistance recommended
|  | Obtaining the technical conditions, urban planning conditions and restrictions, development of assignments for design planning | SJA/ICoS | February/March | No external assistance required
|  | Preparation of required documents with further conduct of tender/procurement processes as well as conclusion of a contract on execution of construction works for reconstruction of HACC buildings | SJA/ICoS | February/March | External assistance is required
| Human Resources | Interim CoS drafts and approves all required legal document to make HACC capable to function: (a)Interim structure and staffing table of HACC; (b)Interim HACC Rules of Procedure or Interim regulation of HACC together with Regulation on created departments and other structural units; (c)Job descriptions of positions to be filled in intermediary stage | ICoS | February/March | External expert assistance recommended | Checklist for promoting the quality of judges and courts, CEPEJ 2008 (section IV); CQFD Handbook on Quality of Justice; HACC Judicial Administration Resource Materials (Chemonics)
|  | Identification and transferring of essential positions needed to be filled by the interim CoS for the initial stage of HACC setting up and functioning | ICoS | February/March | External expert assistance recommended
|  | Needs assessment/roadmap for development of immediate, medium and long-term HR strategy for HACC | ICoS | February/March | External expert assistance recommended | Checklist for promoting the quality of judges and courts, CEPEJ 2008 (section IV)
| IT support & Security | Conduct needs assessment for identifying immediate, medium and long-term needs. | SJA/ICoS | February/March | External expert assistance recommended
| Furniture/ Equipment Infrastructure | Development of a plan for purchasing furniture, equipment and technology | SJA/ICoS | February/March | External expert assistance is recommended | US Courts design guide (2007)
| Court Security | Undertaking situation and needs assessment of new HACC premises | SJA/ICoS | February/March | External expert assistance highly recommended | Guidelines for Implementing Best Practices in Court Building Security, National Center for State Courts, 2010; CCJ/COSCA Court Security Handbook, 2012
|  | Development of HACC buildings security design | SJA/ICoS | February/March | External expert assistance highly recommended | Guidelines for Implementing Best Practices in Court Building Security, National Center for State Courts, 2010; CCJ/COSCA Court Security Handbook, 2012
|  | Appoint head of Judicial Security Service (JSS) | HCJ/SJA | February | No external assistance required
|  | Development/Approval of a structure for JSS and relevant legal documents | Head of JSS | February/March | External expert assistance recommended
Phase 3 | Infrastructure | Development of a project for the reconstruction of buildings, performance of a comprehensive expert examination of design and estimate documentation and receiving of an appropriate summary | SJA/ICoS | March/April | External expert assistance highly recommended | US Courts design guide (2007) Judicial Conference of the US
|  | Preparation of required documents with further conduct of tender/procurement processes as well as conclusion of a contract on execution of construction works for reconstruction of HACC buildings | SJA/ICoS | March/April | External assistance is required
| Human Resources | Development of immediate and mid-term strategy for initial and continuous training and training curricula for judges and staff of the HACC | ICoS/National School of Judges | February/March | External expert assistance highly recommended | Draft Judicial Administration Leadership Program for HACC staff (Chemonics)
| IT Support & Security | Based on needs assessment, development of a strategy/action plan for immediate, medium and long-term needs for both software and hardware | SJA/ICoS | March | External assistance highly recommended
|  | Development of ToR (technical offer) for procurement/development of hardware and software, including technical capacity for storing, managing, archiving documents, security and interoperability of the systems of criminal justice chain and interfaces | SJA/ICoS | March | External assistance highly recommended
|  | Procurement procedure for hardware and software required | SJA/ICoS | March | External assistance recommended
|  | Development of immediate and mid-term strategy for initial and continuous training and training curricula | ICoS | March | External expert assistance recommended
| Furniture/Equipment Infrastructure | Development of a plan for purchasing furniture, equipment and technology | SJA/ICoS | February/March | External expert assistance is recommended | US Courts design guide (2007)
| Court Security | Development of ToR (technical offer) for HACC premises security design and + necessary equipment, including for home security of judges. Tendering /Awarding contract. Alternative: Outsource home security services for judges to the special structural unit tasked with security of particular institutions (Protection Police/поліція охорони) | SJA/ICoS | March | External expert assistance highly recommended
|  | Draft a comprehensive security policy/strategy for HACC | JSS/ICoS | March | External expert assistance highly recommended | Guidelines for Implementing Best Practices in Court Building Security, National Center for State Courts, 2010; CCJ/COSCA Court Security Handbook, 2012
|  | Development of Guidelines for implementing best practices in court building including security risk management methodology and standard operational procedure (SOP) for potential threat scenarios | SJA/ICoS/JSS | March | External expert assistance highly recommended | Guidelines for Implementing Best Practices in Court Building Security, National Center for State Courts, 2010; CCJ/COSCA Court Security Handbook, 2012
|  | Development of a strategy for security for judges and their family members outside the HACC premises | SJA/ICoS/JSS/National Police/National Guard | March | External expert assistance highly recommended | CCJ/COSCA Court Security Handbook, 2012 (Appendix C)
|  | Development of job descriptions and qualification requirements for all positions at JSS | Head of JSS | March | External expert assistance recommended
|  | Commencement of a recruitment process for JSS | HCJ- A category of staff SJA – B, C categories | February/March | No external assistance required
|  | Development of immediate and mid-term strategy for initial and continuous training and training curricula | SJA/ICoS/JSS | March/April | External expert assistance recommended
| Communication & PR | Development of communication & PR strategy with communication matrix addressing: public and media access to court proceedings, access to judgements and other court-related information, access and dissemination of legal information, public awareness raising and outreach | ICoS/Head of the relevant unit | March | External expert assistance highly recommended | CQFD Handbook on Quality of Justice, Scoreboard for the quality of justice; Resource guide on strengthening judicial integrity and capacity, UNDOC 2011
|  | Creating interactive web site of HACC | ICoS/Outsourced company (optional) | March | External expert assistance highly recommended
|  | Development of immediate and mid-term strategy for initial and continuous training and training curricula | ICoS/National School of Judges | March | External expert assistance highly recommended
| Caseflow Management | Assessment of existing: systems and practices of assignments of criminal cases and of judicial calendars; management of cases; management of pre-trial events and trial court hearings; management of timeframes, compliance with time standards; system of collecting monitoring and evaluation of court statistics and of measuring court performance Recommendations on improvement case management system and practices of HACC | Leadership of selected criminal court | March | External expert assistance highly recommended | Corruption prevention; Members of Parliament, Judges and Prosecutors, Conclusions and trends, GRECO, 2017; Resource guide on strengthening judicial integrity and capacity, UNDOC 2011 (Chapter V) Caseflow Management, NCSC, 2002
|  | Development of a plan for improving case management policy and practices of HAAC and judges | Leadership of HACC | March | External expert assistance highly recommended
Phase 4 | Caseflow Management | Development of a plan for improving case management policy and practices of HACC and judges | Leadership of HACC | May | External expert assistance highly recommended
|  | Establishing a system of regular monitoring and evaluation of performance of HACC. (clearance rate, case turnover ratio, disposition time and other performance indicators) | Leadership of HACC | May | External expert assistance highly recommended | Saturn Guidelines for judicial time management, CEPEJ , The Court Tools System, NCSC; EU Justice Scoreboard
|  | Obtaining permits and start of construction works for reconstruction of HACC buildings | SJA/ICoS | March | No external assistance required
| Infrastructure | Completion of construction works of HACC buildings and putting them into operation | SJA/ICoS | September
| Furniture/Equipment Infrastructure | Procurement procedure | ICoS | March | External assistance is required
|  | Room equipment (rooms, courtrooms etc.) to work with information which is a state secret | ICoS | March | No external assistance required
| Court Security | Installing all necessary equipment in HACC and judges’ homes | ICoS/JSS | September | No external assistance required
|  | Implement initial training sessions | Head of JSS | March | External expert assistance recommended
| Human Resources | Open call for a competition of permanent HACC CoS | SJA/ICoS/HCJ | After the HACC President is selected | No external assistance required
|  | Permanent CoS prepares and approves all legal documents necessary to ensure the proper functioning of HACC: (a) Structure and staffing table of HACC (b)Regulation of HACC (c)Regulation on created departments and other structural units (d)Job descriptions of positions | HACC CoS (Permanent Chief of Staff) | within 10 days after CoS is appointed | External expert assistance recommended | Checklist for promoting the quality of judges and courts, CEPEJ 2008 (section IV); CQFD Handbook on Quality of Justice; HACC Judicial Administration Resource Materials (Chemonics)
|  | Open call for a competition of permanent HACC staff | SJA/CoS/HCJ | within 30 days after CoS is appointed | No external assistance required
| Communication & PR | Identification of a judge/PR contact point | President of the HACC | May | No external assistance required
|  | Implementation of initial training sessions | ICoS | May | External expert assistance highly recommended
Phase 5 | Human Resources | Development and implementation of long term strategy for training and training curricula for judges and staff of HACC | SJA/CoS/National School of Judges | June | External expert assistance highly recommended
| IT Support & Security | Further development and implementation of long term strategies to strengthen IT and IT security systems. | CoS | June | External assistance highly recommended
|  | Implementation of long term IT and IT security training program | SJA/CoS/National School of Judges | June | External assistance highly recommended